## WB! Status
What'sBest!® 16.0.2.5 (Aug 20, 2019) - Lib.:12.0.3977.188 - 64-bit - Status Report -
- Lindo Staff -
DATE GENERATED: | 2020-01-28 11:42 | 43858.4875
MODEL INFORMATION:
CLASSIFICATION DATA Current Capacity Limits
--------------------------------------------------------
Total Cells 327
Numerics 306
Adjustables 55 Unlimited
Continuous 0
Free 0
Integers/Binaries 0/55 Unlimited
Constants 149
Formulas 102
Strings 0
Constraints 21 Unlimited
Nonlinears 0 Unlimited
Coefficients 779
Minimum coefficient value: 0.18690715018667 on Model!T24
Minimum coefficient in formula: Model!G26
Maximum coefficient value: 12 on Model!H14
Maximum coefficient in formula: Model!H21
MODEL TYPE: | Mixed Integer / Linear (Mixed Integer Linear Program)
SOLUTION STATUS: | GLOBALLY OPTIMAL
OBJECTIVE VALUE: | 20.9345
BEST OBJECTIVE BOUND: | 20.9345
OPTIMALITY TOLERANCES: | 1e-05
INFEASIBILITY: | 8.8818e-16
DIRECTION: | Maximize
SOLVER TYPE: | Branch-and-Bound
ITERATIONS: | 129
STEPS: | 0
ACTIVE: | 0
SOLUTION TIME: | 0 Hours 0 Minutes 0 Seconds
Extracting Data | 0 Hours 0 Minutes 0 Seconds
Storing Relevant Formulas | 0 Hours 0 Minutes 0 Seconds
Building the Model | 0 Hours 0 Minutes 0 Seconds
Solving | 0 Hours 0 Minutes 0 Seconds
NON-DEFAULT SETTINGS:
WBBIN Range: Detected
End of Report

## Model
Project Start Planning in What'sBest!
We have a set of projects, each with a given set of cash flows. | [7 empty] | Cash Flow if started in Period 1 |  |  |  |  | Periods
When should we start each project? | [5 empty] | Project | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16
so as to Maximize Net present value, subject to | [5 empty] | A | -10 | -1 | 5 | 6 | 7 | 3 | 2 | 1 | 2 | 3 | 4 | 0 | 0 | 0 | 0 | 0
various constraints on what combinations of projects | [5 empty] | B | -9 | 7 | 5 | 2 | -3 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 0 | 0 | 0 | 0
can start when. | [5 empty] | C | -9 | 4 | 6 | 2 | -3 | 1 | 2 | 3 | 4 | 5 | 0 | 0 | 0 | 0 | 0 | 0
Keywords: Multi-period, Project planning; | [5 empty] | D | -12 | 1 | 5 | 6 | 7 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | E | 8 | -1 | -2 | -3 | -2 | -2 | -1 | -2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Can do project | Project
|  |  | at most once. | used? |  |  | Decision variables. A "1" appears in the period in which project starts. | [10 empty] | Fix at 0 if do not allow start after specific period.
|  |  | =>= | 1 |  | A | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | =>= | 1 |  | B | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | =>= | 1 |  | C | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | =>= | 1 |  | D | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | =>= | 1 |  | E | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Shifted Cash Flows based on start period. (This formula is tedious, but need enter only initially, then copy)
[6 empty] | A | -10 | -1 | 5 | 6 | 7 | 3 | 2 | 1 | 2 | 3 | 4 | 0 | 0 | 0 | 0 | 0
[6 empty] | B | -9 | 7 | 5 | 2 | -3 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 0 | 0 | 0 | 0
[6 empty] | C | 0 | -9 | 4 | 6 | 2 | -3 | 1 | 2 | 3 | 4 | 5 | 0 | 0 | 0 | 0 | 0
[6 empty] | D | 0 | 0 | -12 | 1 | 5 | 6 | 7 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0
| 0.15 | <<-- Interest rate |  |  |  | E | 8 | -1 | -2 | -3 | -2 | -2 | -1 | -2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | Total cash flow in period: | -11 | -4 | 0 | 12 | 9 | 5 | 11 | 7 | 11 | 13 | 15 | 7 | 0 | 0 | 0 | 0
[6 empty] | Discount factor: | 1 | 0.86957 | 0.75614 | 0.65752 | 0.57175 | 0.49718 | 0.43233 | 0.37594 | 0.3269 | 0.28426 | 0.24718 | 0.21494 | 0.18691 | 0.16253 | 0.14133 | 0.12289
[5 empty] | NPV, to be maximized: | 20.9345
Here are some example application specific constraints:
Constraint: Total cash flow in period cannot be more negative than budget:
|  | 11 | <<-- Budget |  |  |  | =<= | <= | <= | <= | <= | <= | <= | <= | <= | <= | <= | <= | <= | <= | <= | <=