## WB! Status
What'sBest!® 16.0.2.5 (Aug 20, 2019) - Lib.:12.0.3977.168 - 64-bit - Status Report -
- Lindo Staff -
DATE GENERATED: | 2019-11-03 13:23 | 43772.5576
MODEL INFORMATION:
CLASSIFICATION DATA Current Capacity Limits
--------------------------------------------------------
Total Cells 261
Numerics 143
Adjustables 30 Unlimited
Continuous 30
Free 0
Integers/Binaries 0/0 Unlimited
Constants 46
Formulas 67
Strings 84
Constraints 34 Unlimited
Nonlinears 0 Unlimited
Coefficients 248
Minimum coefficient value: 1 on Nodes!G8
Minimum coefficient in formula: Nodes!G8
Maximum coefficient value: 160 on Nodes!F12
Maximum coefficient in formula: Nodes!E25
MODEL TYPE: | Linear (Linear Program)
SOLUTION STATUS: | GLOBALLY OPTIMAL
OBJECTIVE VALUE: | 140
BEST OBJECTIVE BOUND: | . . .
INFEASIBILITY: | 0
DIRECTION: | Minimize
SOLVER TYPE: | . . .
ITERATIONS: | 4
STEPS: | . . .
ACTIVE: | . . .
SOLUTION TIME: | 0 Hours 0 Minutes 0 Seconds
Extracting Data | 0 Hours 0 Minutes 0 Seconds
Storing Relevant Formulas | 0 Hours 0 Minutes 0 Seconds
Building the Model | 0 Hours 0 Minutes 0 Seconds
Solving | 0 Hours 0 Minutes 0 Seconds
NON-DEFAULT SETTINGS:
String Support: On (limited support of string operations)
End of Report

## Nodes
Crashing analysis for Reliable Construction
If all tasks in a project network, the project will finish later than its deadline.
If each task can be shortened at a given cost/day shortened, which tasks
should be shortend ("crashed") so the project meets its duedate at minimum cost?
(UL on crashing)= maximum number days a task can be shortened
|  | Normal | UL on | Crash cost | Days | Actual | UL on | Start | Finish
| Activity/task | Duration | crashing | per day | Crashed | Duration | crashing | time | time
| A | 2 | 1 | 100 | 0 | 2 | <= | 0 | 2
| B | 4 | 2 | 50 | 0 | 4 | <= | 2 | 6
| C | 10 | 3 | 80 | 0 | 10 | <= | 6 | 16
| D | 6 | 2 | 40 | 0 | 6 | <= | 16 | 22
| E | 4 | 1 | 160 | 0 | 4 | <= | 16 | 20
| F | 5 | 2 | 40 | 2 | 3 | =<= | 20 | 23
| G | 7 | 3 | 40 | 0 | 7 | <= | 22 | 29
| H | 9 | 3 | 60 | 0 | 9 | <= | 29 | 38
| I | 7 | 2 | 30 | 0 | 7 | <= | 16 | 23
| J | 8 | 2 | 30 | 2 | 6 | =<= | 23 | 29
| K | 4 | 1 | 40 | 0 | 4 | <= | 29 | 33
| L | 5 | 2 | 50 | 0 | 5 | <= | 29 | 34
| M | 2 | 1 | 100 | 0 | 2 | <= | 38 | 40
| N | 6 | 3 | 60 | 0 | 6 | <= | 34 | 40
| FINISH | 0 | 0 | 0 | 0 | 0 | =<= | 40 | 40
|  |  | Total cost of crashing: | 140 | <<==Minimize
|  |  | DUEDATE= | 40
|  |  | Last task must finish by duedate: | =<=
Keywords: CPM, Crashing, PERT, Project management

## Arcs
Here are the precedence pairs. The first Task in a pair
must be completed before the second can start.
Pred | Succ | FinTime of Pred |  | Start time of Succ
A | B | 2 | =<= | 2
B | C | 6 | =<= | 6
C | D | 16 | =<= | 16
C | E | 16 | =<= | 16
E | F | 20 | =<= | 20
D | G | 22 | =<= | 22
E | H | 20 | <= | 29
G | H | 29 | =<= | 29
C | I | 16 | =<= | 16
F | J | 23 | =<= | 23
I | J | 23 | =<= | 23
J | K | 29 | =<= | 29
J | L | 29 | =<= | 29
H | M | 38 | =<= | 38
K | N | 33 | <= | 34
L | N | 34 | =<= | 34
M | FINISH | 40 | =<= | 40
N | FINISH | 40 | =<= | 40